Gantt

| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| May 18-24 | May 25-31 | Jun 1-7 | Jun 8-14 | Jun 15-21 | Jun 22-28 | Jun 29-Jul 5 | Jul 6-12 | Jul 13-19 | Jul 20-26 |

Completed Work and Near-Term Transition

| Task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project charter |  |  |  |  |  |  |  |  |  |  | Project scope, deliverables, initial plan. |
| Team charter |  |  |  |  |  |  |  |  |  |  | Roles, expectations, communication. |
| Customer requirements / engineering specs |  |  |  |  |  |  |  |  |  |  | Portable, low-cost, offline-capable tracking system. |
| Initial architecture / block diagram |  |  |  |  |  |  |  |  |  |  | Hider, Seeker, LoRa, BLE, GPS, NUC, MQTT, Node-RED. |
| Hardware platform and integrations |  |  |  |  |  |  |  |  |  |  | T-Beams, NUC/laptop, MQTT, logging, maps. |
| LoRa GPS design |  |  |  |  |  |  |  |  |  |  | Packet design and LoRa/GPS architecture. |
| Build Hider/Seeker LoRa communication |  |  |  |  |  |  |  |  |  |  | Basic LoRa TX/RX working. |
| GPS-over-LoRa implementation |  |  |  |  |  |  |  |  |  |  | Hider GPS transmitted and Seeker parsed it. |
| LoRa RSSI long-range foxhunting |  |  |  |  |  |  |  |  |  |  | No-GPS long-range hot/cold tracking. |
| BLE close-range foxhunting |  |  |  |  |  |  |  |  |  |  | Close-range tracking and LoRa-to-BLE handoff. |
| Hider motion detection and case |  |  |  |  |  |  |  |  |  |  | Motion detection started; 3D case completed. |
| Node-RED/MQTT mapping integration |  |  |  |  |  |  |  |  |  |  | Laptop and NUC mapping pipeline established. |
| JSON telemetry and logging |  |  |  |  |  |  |  |  |  |  | Seeker outputs JSON; CSV/SQL logging explored. |
| NUC hotspot and wireless mapping |  |  |  |  |  |  |  |  |  |  | Battery NUC hotspot and wireless Seeker telemetry working. |
| Initial offline map investigation |  |  |  |  |  |  |  |  |  |  | Offline mapping research and first attempts. |
| Distance and bearing refinement |  |  |  |  |  |  |  |  |  |  | Polish GPS-to-GPS distance and bearing. |
| Map display improvements |  |  |  |  |  |  |  |  |  |  | Labels, map line, clearer Hider/Seeker visualization. |
| GPS / LoRa RSSI / BLE RSSI filtering |  |  |  |  |  |  |  |  |  |  | Moving average/median/weighted smoothing. |
| Navigation guidance |  |  |  |  |  |  |  |  |  |  | Closer/farther, bearing, direction prompts. |
| LoRa-to-BLE handoff tuning and tests |  |  |  |  |  |  |  |  |  |  | Field test long-range LoRa and close-range BLE. |
| Motion alerting fix |  |  |  |  |  |  |  |  |  |  | Alert thresholds, false alert reduction, telemetry output. |
| Hider battery / sleep optimization |  |  |  |  |  |  |  |  |  |  | Wake-on-move, periodic chirps, longer sleep life. |
| Offline mapping integration |  |  |  |  |  |  |  |  |  |  | Offline/cached local map for NUC field system. |
| End-to-end field testing |  |  |  |  |  |  |  |  |  |  | Hider-Seeker-NUC-map test with logging. |
| Direction-finding attempt |  |  |  |  |  |  |  |  |  |  | RSSI/antenna direction finding evaluation. |
| Directional RSSI data collection |  |  |  |  |  |  |  |  |  |  | Collect and analyze LoRa/BLE directional signal data. |
| Test data analysis vs requirements |  |  |  |  |  |  |  |  |  |  | Compare performance to requirements and limitations. |
| Final system refinement |  |  |  |  |  |  |  |  |  |  | Stabilize firmware, mapping, navigation, and demo flow. |
| Final demo / report / presentation |  |  |  |  |  |  |  |  |  |  | Final test results, cost, lessons learned, future work. |